## Budget Final
|  | TOTAL | TOTAL
Task Number | TASK Description | HOURS | COST | RATE ($/hr) | Week1 |  |  | Week2 |  |  | Week3 |  |  | Week4 |  |  | Week5 |  |  | Week6 |  |  | Week7 |  |  | Week8 |  |  | Week9 |  |  | Week10 |  |  | Week11 |  |  | Week12 | Week13 | Week14
1 | Initiation Phase | 144 | 4960 |  | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 32 | 1600 | 50 | Kunja | 8 | 400 | Kunja | 24 | 1200
| Team member 1 | 16 | 480 | 30 | Xiangyi | 8 | 240 | Xiangyi | 8 | 240
| Team member 2 | 16 | 480 | 30 | Yaxin | 8 | 240 | Yaxin | 8 | 240
| Team member 3 | 16 | 480 | 30 | Samarpita | 8 | 240 | Samarpita | 8 | 240
| Team member 4 | 16 | 480 | 30 | Shoeb | 8 | 240 | Shoeb | 8 | 240
| Team member 5 | 16 | 480 | 30 | Prasraban | 8 | 240 | Prasraban | 8 | 240
| Team member 6 | 16 | 480 | 30 | Pratarshi | 8 | 240 | Pratarshi | 8 | 240
| Team member 7 | 16 | 480 | 30 | Debaleena | 8 | 240 | Debaleena | 8 | 240
1.1 | Project Charter Documentation | 64 | 2080 |  | Resource | Hours | Total ($)
| Project Manager | 8 | 400 | 50 | Kunja | 8 | 400
| Team member 1 | 8 | 240 | 30 | Xiangyi | 8 | 240
| Team member 2 | 8 | 240 | 30 | Yaxin | 8 | 240
| Team member 3 | 8 | 240 | 30 | Samarpita | 8 | 240
| Team member 4 | 8 | 240 | 30 | Shoeb | 8 | 240
| Team member 5 | 8 | 240 | 30 | Prasraban | 8 | 240
| Team member 6 | 8 | 240 | 30 | Pratarshi | 8 | 240
| Team member 7 | 8 | 240 | 30 | Debaleena | 8 | 240
1.2 | Project Charter Signoff | 16 | 800 |  |  |  |  | Resource | Hours | Total ($)
| Project Manager | 16 | 800 | 50 |  |  |  | Kunja | 16 | 800
| Team member 1 | 0 | 0 | 30 |  |  |  | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 |  |  |  | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 |  |  |  | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 |  |  |  | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 |  |  |  | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 |  |  |  | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 |  |  |  | Debaleena | 0 | 0
1.3 | Kickoff Meeting | 64 | 2080 |  |  |  |  | Resource | Hours | Total ($)
| Project Manager | 8 | 400 | 50 |  |  |  | Kunja | 8 | 400
| Team member 1 | 8 | 240 | 30 |  |  |  | Xiangyi | 8 | 240
| Team member 2 | 8 | 240 | 30 |  |  |  | Yaxin | 8 | 240
| Team member 3 | 8 | 240 | 30 |  |  |  | Samarpita | 8 | 240
| Team member 4 | 8 | 240 | 30 |  |  |  | Shoeb | 8 | 240
| Team member 5 | 8 | 240 | 30 |  |  |  | Prasraban | 8 | 240
| Team member 6 | 8 | 240 | 30 |  |  |  | Pratarshi | 8 | 240
| Team member 7 | 8 | 240 | 30 |  |  |  | Debaleena | 8 | 240
1.4 | Project Initiated | 0 | 0 |  |  |  |  | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 |  |  |  | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 |  |  |  | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 |  |  |  | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 |  |  |  | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 |  |  |  | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 |  |  |  | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 |  |  |  | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 |  |  |  | Debaleena | 0 | 0
2 | Planning Phase | 192 | 6240 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 24 | 1200 | 50 | [6 empty] | Kunja | 24 | 1200
| Team member 1 | 24 | 720 | 30 | [6 empty] | Xiangyi | 24 | 720
| Team member 2 | 24 | 720 | 30 | [6 empty] | Yaxin | 24 | 720
| Team member 3 | 24 | 720 | 30 | [6 empty] | Samarpita | 24 | 720
| Team member 4 | 24 | 720 | 30 | [6 empty] | Shoeb | 24 | 720
| Team member 5 | 24 | 720 | 30 | [6 empty] | Prasraban | 24 | 720
| Team member 6 | 24 | 720 | 30 | [6 empty] | Pratarshi | 24 | 720
| Team member 7 | 24 | 720 | 30 | [6 empty] | Debaleena | 24 | 720
2.1 | Operations Planning | 64 | 2080 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 8 | 400 | 50 | [6 empty] | Kunja | 8 | 400
| Team member 1 | 8 | 240 | 30 | [6 empty] | Xiangyi | 8 | 240
| Team member 2 | 8 | 240 | 30 | [6 empty] | Yaxin | 8 | 240
| Team member 3 | 8 | 240 | 30 | [6 empty] | Samarpita | 8 | 240
| Team member 4 | 8 | 240 | 30 | [6 empty] | Shoeb | 8 | 240
| Team member 5 | 8 | 240 | 30 | [6 empty] | Prasraban | 8 | 240
| Team member 6 | 8 | 240 | 30 | [6 empty] | Pratarshi | 8 | 240
| Team member 7 | 8 | 240 | 30 | [6 empty] | Debaleena | 8 | 240
2.1.1 | Task Identification | 32 | 960 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [6 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [6 empty] | Xiangyi | 0 | 0
| Team member 2 | 8 | 240 | 30 | [6 empty] | Yaxin | 8 | 240
| Team member 3 | 8 | 240 | 30 | [6 empty] | Samarpita | 8 | 240
| Team member 4 | 8 | 240 | 30 | [6 empty] | Shoeb | 8 | 240
| Team member 5 | 0 | 0 | 30 | [6 empty] | Prasraban | 0 | 0
| Team member 6 | 8 | 240 | 30 | [6 empty] | Pratarshi | 8 | 240
| Team member 7 | 0 | 0 | 30 | [6 empty] | Debaleena | 0 | 0
2.1.2 | Task Assignment | 8 | 400 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 8 | 400 | 50 | [6 empty] | Kunja | 8 | 400
| Team member 1 | 0 | 0 | 30 | [6 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [6 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [6 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [6 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [6 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [6 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [6 empty] | Debaleena | 0 | 0
2.1.3 | Task Dependency and Priority | 24 | 720 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [6 empty] | Kunja | 0 | 0
| Team member 1 | 8 | 240 | 30 | [6 empty] | Xiangyi | 8 | 240
| Team member 2 | 0 | 0 | 30 | [6 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [6 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [6 empty] | Shoeb | 0 | 0
| Team member 5 | 8 | 240 | 30 | [6 empty] | Prasraban | 8 | 240
| Team member 6 | 0 | 0 | 30 | [6 empty] | Pratarshi | 0 | 0
| Team member 7 | 8 | 240 | 30 | [6 empty] | Debaleena | 8 | 240
2.2 | Statement of work | 128 | 4160 | [7 empty] | Resource | Hours | Total ($)
| Project Manager | 16 | 800 | 50 | [6 empty] | Kunja | 16 | 800
| Team member 1 | 16 | 480 | 30 | [6 empty] | Xiangyi | 16 | 480
| Team member 2 | 16 | 480 | 30 | [6 empty] | Yaxin | 16 | 480
| Team member 3 | 16 | 480 | 30 | [6 empty] | Samarpita | 16 | 480
| Team member 4 | 16 | 480 | 30 | [6 empty] | Shoeb | 16 | 480
| Team member 5 | 16 | 480 | 30 | [6 empty] | Prasraban | 16 | 480
| Team member 6 | 16 | 480 | 30 | [6 empty] | Pratarshi | 16 | 480
| Team member 7 | 16 | 480 | 30 | [6 empty] | Debaleena | 16 | 480
3 | Research Phase | 776 | 24240 | [10 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 48 | 2400 | 50 | [9 empty] | Kunja | 0 | 0 | Kunja | 8 | 400 | Kunja | 40 | 2000
| Team member 1 | 104 | 3120 | 30 | [9 empty] | Xiangyi | 24 | 720 | Xiangyi | 40 | 1200 | Xiangyi | 40 | 1200
| Team member 2 | 104 | 3120 | 30 | [9 empty] | Yaxin | 24 | 720 | Yaxin | 40 | 1200 | Yaxin | 40 | 1200
| Team member 3 | 104 | 3120 | 30 | [9 empty] | Samarpita | 24 | 720 | Samarpita | 40 | 1200 | Samarpita | 40 | 1200
| Team member 4 | 104 | 3120 | 30 | [9 empty] | Shoeb | 40 | 1200 | Shoeb | 24 | 720 | Shoeb | 40 | 1200
| Team member 5 | 104 | 3120 | 30 | [9 empty] | Prasraban | 40 | 1200 | Prasraban | 24 | 720 | Prasraban | 40 | 1200
| Team member 6 | 104 | 3120 | 30 | [9 empty] | Pratarshi | 24 | 720 | Pratarshi | 40 | 1200 | Pratarshi | 40 | 1200
| Team member 7 | 104 | 3120 | 30 | [9 empty] | Debaleena | 40 | 1200 | Debaleena | 24 | 720 | Debaleena | 40 | 1200
3.1 | Research on the Case | 168 | 5040 | [10 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [9 empty] | Kunja | 0 | 0 | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [9 empty] | Xiangyi | 0 | 0 | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [9 empty] | Yaxin | 0 | 0 | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [9 empty] | Samarpita | 0 | 0 | Samarpita | 0 | 0
| Team member 4 | 56 | 1680 | 30 | [9 empty] | Shoeb | 40 | 1200 | Shoeb | 16 | 480
| Team member 5 | 56 | 1680 | 30 | [9 empty] | Prasraban | 40 | 1200 | Prasraban | 16 | 480
| Team member 6 | 0 | 0 | 30 | [9 empty] | Pratarshi | 0 | 0 | Pratarshi | 0 | 0
| Team member 7 | 56 | 1680 | 30 | [9 empty] | Debaleena | 40 | 1200 | Debaleena | 16 | 480
3.2 | Information Gathering | 224 | 6720 | [10 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [9 empty] | Kunja | 0 | 0 | Kunja | 0 | 0
| Team member 1 | 56 | 1680 | 30 | [9 empty] | Xiangyi | 24 | 720 | Xiangyi | 32 | 960
| Team member 2 | 56 | 1680 | 30 | [9 empty] | Yaxin | 24 | 720 | Yaxin | 32 | 960
| Team member 3 | 56 | 1680 | 30 | [9 empty] | Samarpita | 24 | 720 | Samarpita | 32 | 960
| Team member 4 | 0 | 0 | 30 | [9 empty] | Shoeb | 0 | 0 | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [9 empty] | Prasraban | 0 | 0 | Prasraban | 0 | 0
| Team member 6 | 56 | 1680 | 30 | [9 empty] | Pratarshi | 24 | 720 | Pratarshi | 32 | 960
| Team member 7 | 0 | 0 | 30 | [9 empty] | Debaleena | 0 | 0 | Debaleena | 0 | 0
3.3 | Peer Review Incorporation | 256 | 8320 | [13 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 32 | 1600 | 50 | [12 empty] | Kunja | 8 | 400 | Kunja | 24 | 1200
| Team member 1 | 32 | 960 | 30 | [12 empty] | Xiangyi | 8 | 240 | Xiangyi | 24 | 720
| Team member 2 | 32 | 960 | 30 | [12 empty] | Yaxin | 8 | 240 | Yaxin | 24 | 720
| Team member 3 | 32 | 960 | 30 | [12 empty] | Samarpita | 8 | 240 | Samarpita | 24 | 720
| Team member 4 | 32 | 960 | 30 | [12 empty] | Shoeb | 8 | 240 | Shoeb | 24 | 720
| Team member 5 | 32 | 960 | 30 | [12 empty] | Prasraban | 8 | 240 | Prasraban | 24 | 720
| Team member 6 | 32 | 960 | 30 | [12 empty] | Pratarshi | 8 | 240 | Pratarshi | 24 | 720
| Team member 7 | 32 | 960 | 30 | [12 empty] | Debaleena | 8 | 240 | Debaleena | 24 | 720
3.4 | Analysis Documentation | 128 | 4160 | [16 empty] | Resource | Hours | Total ($)
| Project Manager | 16 | 800 | 50 | [15 empty] | Kunja | 16 | 800
| Team member 1 | 16 | 480 | 30 | [15 empty] | Xiangyi | 16 | 480
| Team member 2 | 16 | 480 | 30 | [15 empty] | Yaxin | 16 | 480
| Team member 3 | 16 | 480 | 30 | [15 empty] | Samarpita | 16 | 480
| Team member 4 | 16 | 480 | 30 | [15 empty] | Shoeb | 16 | 480
| Team member 5 | 16 | 480 | 30 | [15 empty] | Prasraban | 16 | 480
| Team member 6 | 16 | 480 | 30 | [15 empty] | Pratarshi | 16 | 480
| Team member 7 | 16 | 480 | 30 | [15 empty] | Debaleena | 16 | 480
3.5 | Analysis Document Completion | 0 | 0 | [16 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [15 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [15 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [15 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [15 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [15 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [15 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [15 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [15 empty] | Debaleena | 0 | 0
4 | Case Inference Phase | 920 | 29840 | [19 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 112 | 5600 | 50 | [18 empty] | Kunja | 56 | 2800 | Kunja | 40 | 2000 | Kunja | 16 | 800
| Team member 1 | 96 | 2880 | 30 | [18 empty] | Xiangyi | 40 | 1200 | Xiangyi | 40 | 1200 | Xiangyi | 16 | 480
| Team member 2 | 112 | 3360 | 30 | [18 empty] | Yaxin | 56 | 1680 | Yaxin | 40 | 1200 | Yaxin | 16 | 480
| Team member 3 | 112 | 3360 | 30 | [18 empty] | Samarpita | 56 | 1680 | Samarpita | 40 | 1200 | Samarpita | 16 | 480
| Team member 4 | 96 | 2880 | 30 | [18 empty] | Shoeb | 40 | 1200 | Shoeb | 40 | 1200 | Shoeb | 16 | 480
| Team member 5 | 96 | 2880 | 30 | [18 empty] | Prasraban | 40 | 1200 | Prasraban | 40 | 1200 | Prasraban | 16 | 480
| Team member 6 | 184 | 5520 | 30 | [18 empty] | Pratarshi | 96 | 2880 | Pratarshi | 72 | 2160 | Pratarshi | 16 | 480
| Team member 7 | 112 | 3360 | 30 | [18 empty] | Debaleena | 56 | 1680 | Debaleena | 40 | 1200 | Debaleena | 16 | 480
4.1 | Operation Failure Identification | 128 | 4160 | [19 empty] | Resource | Hours | Total ($)
| Project Manager | 16 | 800 | 50 | [18 empty] | Kunja | 16 | 800
| Team member 1 | 16 | 480 | 30 | [18 empty] | Xiangyi | 16 | 480
| Team member 2 | 16 | 480 | 30 | [18 empty] | Yaxin | 16 | 480
| Team member 3 | 16 | 480 | 30 | [18 empty] | Samarpita | 16 | 480
| Team member 4 | 16 | 480 | 30 | [18 empty] | Shoeb | 16 | 480
| Team member 5 | 16 | 480 | 30 | [18 empty] | Prasraban | 16 | 480
| Team member 6 | 16 | 480 | 30 | [18 empty] | Pratarshi | 16 | 480
| Team member 7 | 16 | 480 | 30 | [18 empty] | Debaleena | 16 | 480
4.2 | Systematic Bias Analysis | 216 | 6480 | [19 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [18 empty] | Kunja | 0 | 0 | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [18 empty] | Xiangyi | 0 | 0 | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [18 empty] | Yaxin | 0 | 0 | Yaxin | 0 | 0
| Team member 3 | 72 | 2160 | 30 | [18 empty] | Samarpita | 40 | 1200 | Samarpita | 32 | 960
| Team member 4 | 0 | 0 | 30 | [18 empty] | Shoeb | 0 | 0 | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [18 empty] | Prasraban | 0 | 0 | Prasraban | 0 | 0
| Team member 6 | 72 | 2160 | 30 | [18 empty] | Pratarshi | 40 | 1200 | Pratarshi | 32 | 960
| Team member 7 | 72 | 2160 | 30 | [18 empty] | Debaleena | 40 | 1200 | Debaleena | 32 | 960
4.3 | Resource Utilization Analysis | 168 | 5040 | [19 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [18 empty] | Kunja | 0 | 0 | Kunja | 0 | 0
| Team member 1 | 56 | 1680 | 30 | [18 empty] | Xiangyi | 24 | 720 | Xiangyi | 32 | 960
| Team member 2 | 0 | 0 | 30 | [18 empty] | Yaxin | 0 | 0 | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [18 empty] | Samarpita | 0 | 0 | Samarpita | 0 | 0
| Team member 4 | 56 | 1680 | 30 | [18 empty] | Shoeb | 24 | 720 | Shoeb | 32 | 960
| Team member 5 | 56 | 1680 | 30 | [18 empty] | Prasraban | 24 | 720 | Prasraban | 32 | 960
| Team member 6 | 0 | 0 | 30 | [18 empty] | Pratarshi | 0 | 0 | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [18 empty] | Debaleena | 0 | 0 | Debaleena | 0 | 0
4.4 | Contingency Plan Analysis | 216 | 7920 | [19 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 72 | 3600 | 50 | [18 empty] | Kunja | 40 | 2000 | Kunja | 32 | 1600
| Team member 1 | 0 | 0 | 30 | [18 empty] | Xiangyi | 0 | 0 | Xiangyi | 0 | 0
| Team member 2 | 72 | 2160 | 30 | [18 empty] | Yaxin | 40 | 1200 | Yaxin | 32 | 960
| Team member 3 | 0 | 0 | 30 | [18 empty] | Samarpita | 0 | 0 | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [18 empty] | Shoeb | 0 | 0 | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [18 empty] | Prasraban | 0 | 0 | Prasraban | 0 | 0
| Team member 6 | 72 | 2160 | 30 | [18 empty] | Pratarshi | 40 | 1200 | Pratarshi | 32 | 960
| Team member 7 | 0 | 0 | 30 | [18 empty] | Debaleena | 0 | 0 | Debaleena | 0 | 0
4.5 | Inference Documentation | 192 | 6240 | [22 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 24 | 1200 | 50 | [21 empty] | Kunja | 8 | 400 | Kunja | 16 | 800
| Team member 1 | 24 | 720 | 30 | [21 empty] | Xiangyi | 8 | 240 | Xiangyi | 16 | 480
| Team member 2 | 24 | 720 | 30 | [21 empty] | Yaxin | 8 | 240 | Yaxin | 16 | 480
| Team member 3 | 24 | 720 | 30 | [21 empty] | Samarpita | 8 | 240 | Samarpita | 16 | 480
| Team member 4 | 24 | 720 | 30 | [21 empty] | Shoeb | 8 | 240 | Shoeb | 16 | 480
| Team member 5 | 24 | 720 | 30 | [21 empty] | Prasraban | 8 | 240 | Prasraban | 16 | 480
| Team member 6 | 24 | 720 | 30 | [21 empty] | Pratarshi | 8 | 240 | Pratarshi | 16 | 480
| Team member 7 | 24 | 720 | 30 | [21 empty] | Debaleena | 8 | 240 | Debaleena | 16 | 480
4.6 | Inference Document Complete | 0 | 0 | [25 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [24 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [24 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [24 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [24 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [24 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [24 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [24 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [24 empty] | Debaleena | 0 | 0
5 | Solution Proposal Phase | 536 | 17520 | [25 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 72 | 3600 | 50 | [24 empty] | Kunja | 24 | 1200 | Kunja | 8 | 400 | Kunja | 40 | 2000
| Team member 1 | 64 | 1920 | 30 | [24 empty] | Xiangyi | 24 | 720 | Xiangyi | 16 | 480 | Xiangyi | 24 | 720
| Team member 2 | 72 | 2160 | 30 | [24 empty] | Yaxin | 24 | 720 | Yaxin | 8 | 240 | Yaxin | 40 | 1200
| Team member 3 | 64 | 1920 | 30 | [24 empty] | Samarpita | 24 | 720 | Samarpita | 16 | 480 | Samarpita | 24 | 720
| Team member 4 | 64 | 1920 | 30 | [24 empty] | Shoeb | 24 | 720 | Shoeb | 16 | 480 | Shoeb | 24 | 720
| Team member 5 | 64 | 1920 | 30 | [24 empty] | Prasraban | 24 | 720 | Prasraban | 16 | 480 | Prasraban | 24 | 720
| Team member 6 | 72 | 2160 | 30 | [24 empty] | Pratarshi | 24 | 720 | Pratarshi | 8 | 240 | Pratarshi | 40 | 1200
| Team member 7 | 64 | 1920 | 30 | [24 empty] | Debaleena | 24 | 720 | Debaleena | 16 | 480 | Debaleena | 24 | 720
5.1 | Operation Execution | 192 | 6240 | [25 empty] | Resource | Hours | Total ($)
| Project Manager | 24 | 1200 | 50 | [24 empty] | Kunja | 24 | 1200
| Team member 1 | 24 | 720 | 30 | [24 empty] | Xiangyi | 24 | 720
| Team member 2 | 24 | 720 | 30 | [24 empty] | Yaxin | 24 | 720
| Team member 3 | 24 | 720 | 30 | [24 empty] | Samarpita | 24 | 720
| Team member 4 | 24 | 720 | 30 | [24 empty] | Shoeb | 24 | 720
| Team member 5 | 24 | 720 | 30 | [24 empty] | Prasraban | 24 | 720
| Team member 6 | 24 | 720 | 30 | [24 empty] | Pratarshi | 24 | 720
| Team member 7 | 24 | 720 | 30 | [24 empty] | Debaleena | 24 | 720
5.2 | Systematic Bias Curb | 32 | 960 | [28 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [27 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [27 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [27 empty] | Yaxin | 0 | 0
| Team member 3 | 16 | 480 | 30 | [27 empty] | Samarpita | 16 | 480
| Team member 4 | 0 | 0 | 30 | [27 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [27 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [27 empty] | Pratarshi | 0 | 0
| Team member 7 | 16 | 480 | 30 | [27 empty] | Debaleena | 16 | 480
5.3 | Resource Optimization | 48 | 1440 | [28 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [27 empty] | Kunja | 0 | 0
| Team member 1 | 16 | 480 | 30 | [27 empty] | Xiangyi | 16 | 480
| Team member 2 | 0 | 0 | 30 | [27 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [27 empty] | Samarpita | 0 | 0
| Team member 4 | 16 | 480 | 30 | [27 empty] | Shoeb | 16 | 480
| Team member 5 | 16 | 480 | 30 | [27 empty] | Prasraban | 16 | 480
| Team member 6 | 0 | 0 | 30 | [27 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [27 empty] | Debaleena | 0 | 0
5.4 | Contingency Plan Proposals | 72 | 2640 | [28 empty] | Resource | Hours | Total ($) | Resource | Hours | Total ($)
| Project Manager | 24 | 1200 | 50 | [27 empty] | Kunja | 8 | 400 | Kunja | 16 | 800
| Team member 1 | 0 | 0 | 30 | [27 empty] | Xiangyi | 0 | 0 | Xiangyi | 0 | 0
| Team member 2 | 24 | 720 | 30 | [27 empty] | Yaxin | 8 | 240 | Yaxin | 16 | 480
| Team member 3 | 0 | 0 | 30 | [27 empty] | Samarpita | 0 | 0 | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [27 empty] | Shoeb | 0 | 0 | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [27 empty] | Prasraban | 0 | 0 | Prasraban | 0 | 0
| Team member 6 | 24 | 720 | 30 | [27 empty] | Pratarshi | 8 | 240 | Pratarshi | 16 | 480
| Team member 7 | 0 | 0 | 30 | [27 empty] | Debaleena | 0 | 0 | Debaleena | 0 | 0
5.5 | Solution Documentation | 192 | 6240 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 24 | 1200 | 50 | [30 empty] | Kunja | 24 | 1200
| Team member 1 | 24 | 720 | 30 | [30 empty] | Xiangyi | 24 | 720
| Team member 2 | 24 | 720 | 30 | [30 empty] | Yaxin | 24 | 720
| Team member 3 | 24 | 720 | 30 | [30 empty] | Samarpita | 24 | 720
| Team member 4 | 24 | 720 | 30 | [30 empty] | Shoeb | 24 | 720
| Team member 5 | 24 | 720 | 30 | [30 empty] | Prasraban | 24 | 720
| Team member 6 | 24 | 720 | 30 | [30 empty] | Pratarshi | 24 | 720
| Team member 7 | 24 | 720 | 30 | [30 empty] | Debaleena | 24 | 720
5.6 | Proposed Solution Document | 0 | 0 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [30 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [30 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [30 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [30 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [30 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [30 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [30 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [30 empty] | Debaleena | 0 | 0
6 | Project Closure Phase | 320 | 10400 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 40 | 2000 | 50 | [30 empty] | Kunja | 40 | 2000
| Team member 1 | 40 | 1200 | 30 | [30 empty] | Xiangyi | 40 | 1200
| Team member 2 | 40 | 1200 | 30 | [30 empty] | Yaxin | 40 | 1200
| Team member 3 | 40 | 1200 | 30 | [30 empty] | Samarpita | 40 | 1200
| Team member 4 | 40 | 1200 | 30 | [30 empty] | Shoeb | 40 | 1200
| Team member 5 | 40 | 1200 | 30 | [30 empty] | Prasraban | 40 | 1200
| Team member 6 | 40 | 1200 | 30 | [30 empty] | Pratarshi | 40 | 1200
| Team member 7 | 40 | 1200 | 30 | [30 empty] | Debaleena | 40 | 1200
6.1 | Case Report Documentation | 256 | 8320 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 32 | 1600 | 50 | [30 empty] | Kunja | 32 | 1600
| Team member 1 | 32 | 960 | 30 | [30 empty] | Xiangyi | 32 | 960
| Team member 2 | 32 | 960 | 30 | [30 empty] | Yaxin | 32 | 960
| Team member 3 | 32 | 960 | 30 | [30 empty] | Samarpita | 32 | 960
| Team member 4 | 32 | 960 | 30 | [30 empty] | Shoeb | 32 | 960
| Team member 5 | 32 | 960 | 30 | [30 empty] | Prasraban | 32 | 960
| Team member 6 | 32 | 960 | 30 | [30 empty] | Pratarshi | 32 | 960
| Team member 7 | 32 | 960 | 30 | [30 empty] | Debaleena | 32 | 960
6.2 | Case Presentation | 64 | 2080 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 8 | 400 | 50 | [30 empty] | Kunja | 8 | 400
| Team member 1 | 8 | 240 | 30 | [30 empty] | Xiangyi | 8 | 240
| Team member 2 | 8 | 240 | 30 | [30 empty] | Yaxin | 8 | 240
| Team member 3 | 8 | 240 | 30 | [30 empty] | Samarpita | 8 | 240
| Team member 4 | 8 | 240 | 30 | [30 empty] | Shoeb | 8 | 240
| Team member 5 | 8 | 240 | 30 | [30 empty] | Prasraban | 8 | 240
| Team member 6 | 8 | 240 | 30 | [30 empty] | Pratarshi | 8 | 240
| Team member 7 | 8 | 240 | 30 | [30 empty] | Debaleena | 8 | 240
6.3 | Project Completion | 0 | 0 | [31 empty] | Resource | Hours | Total ($)
| Project Manager | 0 | 0 | 50 | [30 empty] | Kunja | 0 | 0
| Team member 1 | 0 | 0 | 30 | [30 empty] | Xiangyi | 0 | 0
| Team member 2 | 0 | 0 | 30 | [30 empty] | Yaxin | 0 | 0
| Team member 3 | 0 | 0 | 30 | [30 empty] | Samarpita | 0 | 0
| Team member 4 | 0 | 0 | 30 | [30 empty] | Shoeb | 0 | 0
| Team member 5 | 0 | 0 | 30 | [30 empty] | Prasraban | 0 | 0
| Team member 6 | 0 | 0 | 30 | [30 empty] | Pratarshi | 0 | 0
| Team member 7 | 0 | 0 | 30 | [30 empty] | Debaleena | 0 | 0

## Sheet2
Resource | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7 | Week8 | Week9 | Week10 | Week11 | Total
Kunja | 400 | 1200 | 1200 | 0 | 400 | 2000 | 2800 | 2000 | 2000 | 400 | 4000 | 16400
Xiangyi | 240 | 240 | 720 | 720 | 1200 | 1200 | 1200 | 1200 | 1200 | 480 | 1920 | 10320
Yaxin | 240 | 240 | 720 | 720 | 1200 | 1200 | 1680 | 1200 | 1200 | 240 | 2400 | 11040
Samarpita | 240 | 240 | 720 | 720 | 1200 | 1200 | 1680 | 1200 | 1200 | 480 | 1920 | 10800
Shoeb | 240 | 240 | 720 | 1200 | 720 | 1200 | 1200 | 1200 | 1200 | 480 | 1920 | 10320
Prasraban | 240 | 240 | 720 | 1200 | 720 | 1200 | 1200 | 1200 | 1200 | 480 | 1920 | 10320
Pratarshi | 240 | 240 | 720 | 720 | 1200 | 1200 | 2880 | 2160 | 1200 | 240 | 2400 | 13200
Debaleena | 240 | 240 | 720 | 1200 | 720 | 1200 | 1680 | 1200 | 1200 | 480 | 1920 | 10800
Team Total | [6 empty] | 14320 |  |  |  |  | 93200

## Sheet1
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Actual Duration | Duration
Auto Scheduled | Initiation Phase | 6 days | Fri 9/16/16 | Fri 9/23/16 |  |  | 4.69 days | 6 days
Auto Scheduled | Project Charter Documentation | 8 hrs | Fri 9/16/16 | Fri 9/16/16 |  | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 1 day | 8 hrs
Auto Scheduled | Project Charter Signoff | 2 days | Mon 9/19/16 | Tue 9/20/16 | 3 | Kunja Dutta | 2 days | 2 days
Auto Scheduled | Kickoff Meeting | 1 day | Fri 9/23/16 | Fri 9/23/16 | 4 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 1 day | 1 day
Auto Scheduled | Project Initiated | 0 days | Fri 9/23/16 | Fri 9/23/16 | 5 |  | 0 days | 0 days
Auto Scheduled | Planning Phase | 5 days | Mon 9/26/16 | Fri 9/30/16 | 2 |  | 5 days | 5 days
Auto Scheduled | Operations Planning | 3 days | Mon 9/26/16 | Wed 9/28/16 |  |  | 3 days | 3 days
Auto Scheduled | Task Identification | 1 day | Mon 9/26/16 | Mon 9/26/16 | 6 | Pratarshi Saha,Samarpita Chakrabarty,Mohammed Shoeb Ahmed Shakeb,Yaxin Jiang | 1 day | 1 day
Auto Scheduled | Task Assignment | 1 day | Tue 9/27/16 | Tue 9/27/16 | 9 | Kunja Dutta | 1 day | 1 day
Auto Scheduled | Task Dependency and Priority | 1 day | Wed 9/28/16 | Wed 9/28/16 | 10 | Debaleena Saha,Prasraban Mukhopadhyay,Xiangyi Zhang | 1 day | 1 day
Auto Scheduled | Statement of work | 2 days | Thu 9/29/16 | Fri 9/30/16 | 8 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 2 days | 2 days
Auto Scheduled | Research Phase | 15 days | Mon 10/3/16 | Fri 10/21/16 | 7 |  | 15 days | 15 days
Auto Scheduled | Research on the Case | 7 days | Mon 10/3/16 | Tue 10/11/16 | 12 | Debaleena Saha,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay | 7 days | 7 days
Auto Scheduled | Information Gathering | 7 days | Wed 10/5/16 | Thu 10/13/16 |  | Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 7 days | 7 days
Auto Scheduled | Peer Review Incorporation | 4 days | Fri 10/14/16 | Wed 10/19/16 | 15,14 | Debaleena Saha,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 4 days | 4 days
Auto Scheduled | Analysis Documentation | 2 days | Thu 10/20/16 | Fri 10/21/16 | 16 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 2 days | 2 days
Auto Scheduled | Analysis Document Completion | 0 days | Fri 10/21/16 | Fri 10/21/16 | 17 |  | 0 days | 0 days
Auto Scheduled | Case Inference Phase | 12 days | Mon 10/24/16 | Tue 11/8/16 | 13 |  | 0 days | 12 days
Auto Scheduled | Operation Failure Identification | 2 days | Mon 10/24/16 | Tue 10/25/16 | 18 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 2 days
Auto Scheduled | Systematic Bias Analysis | 9 days | Wed 10/26/16 | Thu 11/3/16 | 20 | Debaleena Saha,Samarpita Chakrabarty,Pratarshi Saha | 0 days | 9 days
Auto Scheduled | Resource Utilization Analysis | 7 days | Wed 10/26/16 | Thu 11/3/16 |  | Mohammed Shoeb Ahmed Shakeb,Xiangyi Zhang,Prasraban Mukhopadhyay | 0 days | 7 days
Auto Scheduled | Contingency Plan Analysis | 9 days | Wed 10/26/16 | Thu 11/3/16 |  | Kunja Dutta,Pratarshi Saha,Yaxin Jiang | 0 days | 9 days
Auto Scheduled | Inference Documentation | 3 days | Fri 11/4/16 | Tue 11/8/16 | 23 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 3 days
Auto Scheduled | Inference Document Complete | 0 days | Tue 11/8/16 | Tue 11/8/16 | 24 |  | 0 days | 0 days
Auto Scheduled | Solution Proposal Phase | 13 days | Wed 11/9/16 | Fri 11/25/16 | 19 |  | 0 days | 13 days
Auto Scheduled | Operation Execution | 3 days | Wed 11/9/16 | Fri 11/11/16 | 25 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 3 days
Auto Scheduled | Systematic Bias Curb | 2 days | Mon 11/14/16 | Tue 11/15/16 | 27 | Debaleena Saha,Samarpita Chakrabarty | 0 days | 2 days
Auto Scheduled | Resource Optimization | 2 days | Wed 11/16/16 | Thu 11/17/16 | 28 | Mohammed Shoeb Ahmed Shakeb,Xiangyi Zhang,Prasraban Mukhopadhyay | 0 days | 2 days
Auto Scheduled | Contingency Plan Proposals | 3 days | Fri 11/18/16 | Tue 11/22/16 | 29 | Kunja Dutta,Pratarshi Saha,Yaxin Jiang | 0 days | 3 days
Auto Scheduled | Solution Documentation | 3 days | Wed 11/23/16 | Fri 11/25/16 | 30 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 3 days
Auto Scheduled | Proposed Solution Document | 0 days | Fri 11/25/16 | Fri 11/25/16 | 31 |  | 0 days | 0 days
Auto Scheduled | Project Closure Phase | 5 days | Mon 11/28/16 | Fri 12/2/16 | 26 |  | 0 days | 5 days
Auto Scheduled | Case Report Documentation | 4 days | Mon 11/28/16 | Thu 12/1/16 | 32 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 4 days
Auto Scheduled | Case Presentation | 1 day | Fri 12/2/16 | Fri 12/2/16 | 34 | Debaleena Saha,Kunja Dutta,Mohammed Shoeb Ahmed Shakeb,Prasraban Mukhopadhyay,Pratarshi Saha,Samarpita Chakrabarty,Xiangyi Zhang,Yaxin Jiang | 0 days | 1 day
Auto Scheduled | Project Completion | 0 days | Fri 12/2/16 | Fri 12/2/16 | 35 |  | 0 days | 0 days
Auto Scheduled | Weekly Status Meeting | 50.02 days | Wed 9/21/16 | Wed 11/30/16 |  |  | 0 days | 50.02 days